## Sheet1
XYZ PVT LTD
Task Tracker
Task ID | Client ID | Organization | Task Name | Category | Assigned To | Priority | Start Date | Due Date | Status | Completion % | Sprint | Client Approval | Story Points | Overdue?
1 | 52270 | Surya Pvt Ltd | Wireframe | Client Review | Nandani Bhardwaj | Medium | 2025-08-03 | 2025-08-10 | In Progress | 100% | Sprint 1 | Pending | 2 | NO
2 | 32589 | NextGen Pvt Ltd | Frond-end | Development | Vikas Agrawal | High | 2025-08-05 | 2025-08-08 | To Do | 50% | Sprint 2 | Approved | 3 | NO
3 | 89651 | Capgamini | Back-end | Development | Govind Goyal | Low | 2025-08-06 | 2025-08-10 | Completed | 100% | Sprint 3 | Rejected | 4 | NO
4 | 61684 | Backbenchar Pvt Ltd | Testing | Testing | Aastha Patel | Medium | 2025-08-07 | 2025-08-12 | Waiting Approval | 30% | Sprint 4 | Pending | 5 | NO
5 | 36131 | TCS | App-dev | Development | Dev Hester | Low | 2025-08-08 | 2025-08-13 | In Progress | 25% | Sprint 5 | Approved | 6 | NO
6 | 13132 | Blackrock | Ios-dev | Research | Arnav Goswami | High | 2025-08-09 | 2025-08-15 | To Do | 40% | Sprint 6 | Rejected | 7 | NO
7 | 31333 | Unity | Wireframe | Client Review | Aryan Yadav | Medium | 2025-08-10 | 2025-08-17 | Completed | 38% | Sprint 1 | Pending | 8 | NO
8 | 23351 | Inwinzio Pvt Ltd | Frond-end | Development | Ravi Aacharya | High | 2025-08-11 | 2025-08-14 | Waiting Approval | 36% | Sprint 2 | Approved | 9 | NO
9 | 31366 | Alpha Pvt Ltd | Back-end | Development | Tanu Sharma | Low | 2025-08-12 | 2025-08-16 | In Progress | 34% | Sprint 3 | Rejected | 10 | NO
10 | 18235.3889 | Vasu Enterprises | Testing | Testing | Rahul Deshmukh | Medium | 2025-08-13 | 2025-08-18 | To Do | 32% | Sprint 4 | Pending | 11 | NO
11 | 13626.7556 | Aura Enterprises | App-dev | Research | Ananya Dutta | Low | 2025-08-14 | 2025-08-20 | Completed | 30% | Sprint 5 | Approved | 12 | NO
12 | 52270 | Surya Pvt Ltd | Ios-dev | Development | Vikram Dubey | High | 2025-08-15 | 2025-08-21 | Waiting Approval | 28% | Sprint 6 | Rejected | 13 | NO
13 | 52271 | NextGen Pvt Ltd | Wireframe | Design | Priya Dey | Medium | 2025-08-16 | 2025-08-22 | In Progress | 26% | Sprint 7 | Pending | 1 | NO
14 | 53370 | Capgamini | Frond-end | Client Review | Ajay Desai | High | 2025-08-17 | 2025-08-23 | To Do | 24% | Sprint 8 | Approved | 2 | NO
15 | 53371 | Backbenchar Pvt Ltd | Back-end | Development | Kiran Dalal | Low | 2025-08-18 | 2025-08-25 | Completed | 22% | Sprint 9 | Rejected | 3 | NO
16 | 62218 | TCS | Testing | Testing | Neha Dixit | Medium | 2025-08-19 | 2025-08-26 | Waiting Approval | 20% | Sprint 10 | Pending | 4 | NO
17 | 46312 | Blackrock | App-dev | Development | Siddharth Damle | Low | 2025-08-20 | 2025-08-27 | In Progress | 18% | Sprint 11 | Approved | 5 | NO
18 | 25879 | Unity | Ios-dev | Development | Ritesh Dandekar | High | 2025-08-21 | 2025-08-28 | To Do | 16% | Sprint 12 | Rejected | 6 | NO
19 | 96325 | Inwinzio Pvt Ltd | Wireframe | Client Review | Pallavi Dang | Medium | 2025-08-22 | 2025-08-29 | Completed | 14% | Sprint 13 | Pending | 7 | NO
20 | 85214 | Alpha Pvt Ltd | Frond-end | Development | Sunil Dabholkar | High | 2025-08-23 | 2025-08-30 | Waiting Approval | 12% | Sprint 1 | Approved | 8 | NO
21 | 74125 | Vasu Enterprises | Back-end | Testing | Kavita Dangi | Low | 2025-08-24 | 2025-08-31 | In Progress | 10% | Sprint 2 | Rejected | 9 | NO
22 | 89632 | Aura Enterprises | Testing | Content | Suresh Dugar | Medium | 2025-08-25 | 2025-09-02 | To Do | 8% | Sprint 3 | Pending | 10 | NO
23 | 78945 | Surya Pvt Ltd | App-dev | Research | Shreya Dhawan | Low | 2025-08-26 | 2025-09-03 | Completed | 6% | Sprint 4 | Approved | 11 | NO
24 | 65498 | NextGen Pvt Ltd | Ios-dev | Client Review | Ashwin Dhar | High | 2025-08-27 | 2025-09-04 | Waiting Approval | 30% | Sprint 5 | Rejected | 12 | NO
25 | 77889 | Capgamini | Wireframe | Design | Rupa Dongre | Medium | 2025-08-28 | 2025-09-05 | In Progress | 20% | Sprint 6 | Pending | 13 | NO
26 | 88779 | Backbenchar Pvt Ltd | Frond-end | Development | Gaurav Dhanraj | High | 2025-08-29 | 2025-09-06 | To Do | 10% | Sprint 7 | Approved | 1 | NO
27 | 99887 | TCS | Back-end | Development | Parul Dangwal | Low | 2025-08-30 | 2025-09-07 | Completed | 0% | Sprint 8 | Rejected | 2 | NO
28 | 66554 | Blackrock | Testing | Client Review | Manoj Dholakia | Medium | 2025-08-31 | 2025-09-08 | Waiting Approval | 10% | Sprint 9 | Pending | 3 | NO
29 | 44556 | Unity | App-dev | Development | Sneha Dabas | Low | 2025-09-01 | 2025-09-09 | In Progress | 20% | Sprint 10 | Approved | 4 | NO
30 | 11223 | Inwinzio Pvt Ltd | Ios-dev | Content | Harshita Dalvi | High | 2025-09-02 | 2025-09-10 | To Do | 30% | Sprint 11 | Rejected | 5 | NO
31 | 33221 | Alpha Pvt Ltd | Wireframe | Design | Amit Dey | Medium | 2025-09-03 | 2025-09-11 | Completed | 40% | Sprint 12 | Pending | 6 | NO
32 | 46125 | Vasu Enterprises | Frond-end | Client Review | Sameer Dodhia | High | 2025-09-04 | 2025-09-12 | Waiting Approval | 50% | Sprint 13 | Approved | 7 | NO
33 | 98931 | Aura Enterprises | Back-end | Content | Roshni Dhamecha | Low | 2025-09-05 | 2025-09-13 | In Progress | 60% | Sprint 3 | Rejected | 8 | NO
34 | 25153 | Surya Pvt Ltd | Testing | Content | Sanjay Darji | Medium | 2025-09-06 | 2025-09-14 | To Do | 70% | Sprint 2 | Pending | 9 | NO
35 | 90092 | NextGen Pvt Ltd | App-dev | Development | Preeti Damodar | Low | 2025-09-07 | 2025-09-15 | Completed | 80% | Sprint 6 | Approved | 10 | NO
36 | 76928 | Capgamini | Ios-dev | Research | Rajat Dabas | High | 2025-09-08 | 2025-09-16 | Waiting Approval | 10% | Sprint 1 | Rejected | 11 | NO
37 | 95844 | Backbenchar Pvt Ltd | Wireframe | Research | Sheila D'Costa | Medium | 2025-09-09 | 2025-09-17 | In Progress | 20% | Sprint 2 | Pending | 12 | NO
38 | 50532 | TCS | Frond-end | Development | Pranav Dasgupta | High | 2025-09-10 | 2025-09-18 | To Do | 30% | Sprint 3 | Approved | 13 | NO
39 | 86123 | Blackrock | Back-end | Development | Meera Deshpande | Low | 2025-09-11 | 2025-09-19 | Completed | 40% | Sprint 4 | Rejected | 14 | NO
40 | 62645 | Unity | Testing | Research | Khushboo Gupta | Medium | 2025-09-12 | 2025-09-20 | Waiting Approval | 50% | Sprint 5 | Pending | 15 | NO
41 | 81099 | Inwinzio Pvt Ltd | App-dev | Client Review | Dheeraj Agrawal | Low | 2025-09-13 | 2025-09-21 | In Progress | 60% | Sprint 6 | Approved | 16 | NO
42 | 79958 | Alpha Pvt Ltd | Ios-dev | Deployment | Varun Datta | High | 2025-09-14 | 2025-09-22 | To Do | 70% | Sprint 7 | Rejected | 1 | NO
43 | 83599 | Vasu Enterprises | Wireframe | Design | Lakshmi Deodhar | Medium | 2025-09-15 | 2025-09-23 | Completed | 80% | Sprint 8 | Pending | 2 | NO
44 | 19033 | Aura Enterprises | Frond-end | Client Review | Rakesh Darshan | High | 2025-09-16 | 2025-09-24 | Waiting Approval | 90% | Sprint 9 | Approved | 5 | NO
45 | 86475 | Surya Pvt Ltd | Back-end | Development | Mitali Desai | Low | 2025-09-17 | 2025-09-25 | In Progress | 45% | Sprint 10 | Rejected | 8 | NO
46 | 98975 | NextGen Pvt Ltd | Testing | Client Review | Isha Damani | Medium | 2025-09-18 | 2025-09-26 | To Do | 32% | Sprint 11 | Pending | 9 | NO
47 | 54621 | Capgamini | App-dev | Research | Jayant Dhingra | Low | 2025-09-19 | 2025-09-27 | Completed | 25% | Sprint 12 | Approved | 5 | NO
48 | 10023 | Backbenchar Pvt Ltd | Ios-dev | Research | Lavish Patidar | High | 2025-09-20 | 2025-09-28 | Waiting Approval | 33% | Sprint 13 | Rejected | 1 | NO
49 | 20023 | TCS | Wireframe | Design | Ashika Bhatia | Medium | 2025-09-21 | 2025-09-29 | In Progress | 22% | Sprint 3 | Pending | 3 | NO
50 | 88552 | Blackrock | Frond-end | Deployment | Vinay Mandloi | High | 2025-09-22 | 2025-09-30 | To Do | 11% | Sprint 2 | Approved | 2 | NO
Formulas:
Overdue? = IF(AND([Due Date]<TODAY(),VALUE(SUBSTITUTE([Completion %],"%",""))<100),"YES","NO")